## Project Plan
Workload Assignment
Team Member | Role | Coding Responsibilities | Code Fraction | Additional Tasks
Min Shuen | Database System | Helper and Logical Functions | 30% | Database design, publish
Sarah | User Experience | User Interface Layout (UI in R Shiny) | 20% | Gather data and content for database
Samuel | Backend R Coder | Game State Management | 30%
Yan Ling | Graphics | User Interface | 20% | Source for artwork, testing. Assist in gathering data
Task Dependencies
| Work Breakdown Structure |  |  |  | On Depends | Database design | Data Collection | Game State Management | Helper and Logical Functions | User Interface (UI) | Source Artwork | Testing | Publish | Powerpoint Deliverable
| Tasks | Deadline |  |  | Database design |  | x
| Database design | 2021-03-28 |  |  | Data Collection
| Data Collection | 2021-04-04 |  |  | Game State Management
| Game State Management | 2021-04-04 |  |  | Helper and Logical Functions |  |  | x
| Helper and Logical Functions | 2021-04-10 |  |  | User Interface (UI) |  |  | x |  |  | x
| User Interface (UI) | 2021-04-10 |  |  | Source Artwork |  |  |  |  | x
| Source Artwork | 2021-04-11 |  |  | Testing
| Testing | 2021-04-12 |  |  | Publish | [6 empty] | x
| Publish | 2021-04-14 |  |  | Powerpoint Deliverable
| Powerpoint Deliverable | 2021-04-17